## Slide 1
Change Management Roadmap
AGS
Template

## Slide 2
Sample Change Management Roadmap
Change Execution
Go-Live & Normalization
Assessments &
Solutioning
Jan
Feb
Mar
Apr
Jan
Feb
Mar
May
Jun
Jul
Aug
Sept
Oct
Nov
Dec
Perform Stakeholder Assessment
Conduct Target Audience Analysis
Post Go-Live Communications
Target State Designs & Process Flows
Develop Change Management Plan
Gather Training & Comms Requirements
Develop Training Program & Asset
Broadcast Regular Awareness & Status Update Communications
Perform Go-Live Readiness Assessments of Impacted Organizations
Deliver Training
Go-Live
Conduct Change Impact & Gap Assessment
Go or No-Go Decision
Send out Training Invites & Reminders
Prepare and Broadcast Go-Live Communications
Training Sandbox/UAT Environment is Available
IT Design Documentation
IT Development (Functionalities and Capabilities)
Track Tracking, Comms and Adoption Successes
Pilot Implementation
Prepare Impacted Organizations for Go-Live
Send out Go-Live Get Ready & Countdown Communications
Draft, Socialize and Finalize Awareness Communications
Send Communications about Pilot Implementation & Lessons Learned
Send Communications about the Pilot
Q&A Virtual Sessions | Follow Ups | Add’t Training
Prepare for Change Management Exit. Provide Lessons Learned
Change Management Team Exit/Transition
Q1 2020
Q2 2020
Q3 2020
Q4 2021
Q1 2022
UAT
Training & Readiness
Communication
Normalization
Assessment, Solutioning & Planning
Dependencies
Holidays

## Slide 3
Sample Change Management Roadmap
Change Execution
Go-Live & Normalization
Assessments &
Solutioning
Jan
Feb
Mar
Apr
Jan
Feb
Mar
May
Jun
Jul
Aug
Sept
Oct
Nov
Dec
Perform Stakeholder Assessment
Conduct Target Audience Analysis
Post Go-Live Communications
Target State Designs & Process Flows
Develop Change Management Plan
Gather Training & Comms Requirements
Develop Training Program & Asset
Broadcast Regular Awareness & Status Update Communications
Perform Go-Live Readiness Assessments of Impacted Organizations
Deliver Training
Go-Live
Conduct Change Impact & Gap Assessment
Go or No-Go Decision
Send out Training Invites & Reminders
Prepare and Broadcast Go-Live Communications
Training Sandbox/UAT Environment is Available
IT Design Documentation
IT Development (Functionalities and Capabilities)
Track Tracking, Comms and Adoption Successes
Pilot Implementation
Prepare Impacted Organizations for Go-Live
Send out Go-Live Get Ready & Countdown Communications
Draft, Socialize and Finalize Awareness Communications
Send Communications about Pilot Implementation & Lessons Learned
Send Communications about the Pilot
Q&A Virtual Sessions | Follow Ups | Add’t Training
Prepare for Change Management Exit. Provide Lessons Learned
Change Management Team Exit/Transition
Q1 2020
Q2 2020
Q3 2020
Q4 2021
Q1 2022
UAT
Training & Readiness
Communication
Normalization
Assessment, Solutioning & Planning
Dependencies
Holidays